## 2016-06-27
ID | Priority | Assigned To | State | Title | Description | Comment
1414 | 1 | Matt Corless | Resolved | OCN Peer Review to go to the OSD Originator (don't require assignment) | <p>In the Non-Core OCN process</p>< p>&nbsp;</p>< p>When accepting OCN peer review it went to GK, it should have gone directly to &quot;OSD Originator Review&quot; worked the second time around.</p>< p>&nbsp;</p>< p>Source: Clarence</p><p><br></p><p>Matt: I cannot reproduce this. I believe it was resolved in changeset 9414</p>
1415 | 1 | Matt Corless | Resolved | Advance and Assign broken | <p>In the Non-Core OCN process Advance and Assign didn't work from &quot;Ready for OCN Gov Rev&quot;. It only advanced it, not assigned it.</p>< p>Source: Clarence</p><p><br></p><p>Matt: I believe this has already been fixed in a different changeset and I have not been able to repeat this bug.</p> | Matt: I believe this has already been fixed in a different changeset and I have not been able to repeat this bug.
1439 | 1 | Peter Birch | Resolved | Report is "doubling up" on some states | <p>The report says CORE on some task states doubling up these states. The Core designation is wrong and possibly those are not wanted anyway. Also possibly the first section showing totals could be done in the other direction in columns for each state with the task name down the left and the states across the top with the check or X on the appropriate column.</p>< p>&nbsp;See Clarence for further details.</p>< p>&nbsp;Clarence says no to the page one change, this is a report that Todd created and he gives it to the government monthly and we shouldn't much with it too much as it is a known quantity.</p>
1278 | 1 | Matt Corless | Resolved | Add additional emails | <font face=Arial size=2>< p><font face="Times New Roman" size=3></font><span style="font-family:&quot;Arial&quot;,&quot;sans-serif&quot;;font-size:10pt;">Send emails to people when the drawing shows up in their in-box.<span>&nbsp; </span>Do not send an email to someone who just completed a task and the drawing is being sent to someone else. They said this went to the gatekeeper.</span></p></font><font face="Times New Roman" size=3>< p><span style="font-family:&quot;Arial&quot;,&quot;sans-serif&quot;;font-size:10pt;">Email notifications are not being sent on initial task assignments.</span> </p></font>< p><span style="font-family:&quot;Arial&quot;,&quot;sans-serif&quot;;font-size:10pt;">E</span><span style="font-family:&quot;Arial&quot;,&quot;sans-serif&quot;;font-size:10pt;">mail notifications are not being sent to the Gatekeeper when someone accepts the task.</span><font face="Times New Roman" size=3> </font></p>< p><font face=Arial size=2><font face="Times New Roman" size=3>Core package was assigned to ESG engineer for Gov DI. When he was done it sent an email to Todd. It should have gone to Clarence.</font></font></p>< font face="Times New Roman" size=3><p><font face="Times New Roman" size=3>Source: 2015-09-21 EDT Review (TFS 1292) </font></p></font><font face=Arial size=2>< p><br></p><font face="Times New Roman" size=3>< p><br></p>< p><br></p></font></font>
1284 | 1 | Matt Corless | Resolved | Increase size of input for Hour Log | <p><font face="Times New Roman" size=3>< /font><span style="font-family:&quot;Arial&quot;,&quot;sans-serif&quot;;font-size:10pt;">When editing the time already entered for a specific day, the input window to correct the hours is too small.<span>&nbsp; </span>It needs to show more characters to the right of the input window so that you can see your input.</span><font face="Times New Roman" size=3>< /font></p><p><br></p><p><font face="Times New Roman" size=3>Source: 2015-09-21 EDT Review (TFS 1292) </font></p><p><font face="Times New Roman" size=3>< br>Done - resized, but the modal doesn't validate correctly. It yells at you and still goes away......</font></p>
1356 | 1 | Matt Corless | Resolved | Reject from "Ready for 'OSD Development' Assignment" goes to incorrect state | <p>Non-Core OCN Process</p>< p>&nbsp;Click Reject when in &quot;Ready for 'OSD Development' Assignment&quot; state and it goes rejects to the wrong state. Also - if you ignore that it is in the wrong state and push it forward to the correct state and then do complete/assign it will &quot;dissapear&quot; and not be assigned to anyone.</p>
1357 | 1 | Peter Birch | Resolved | OSD Peer Review/Reject/Complete not auto-assigning | <p>Non-Core OCN Process</p>< p>&nbsp;</p>< p>OSD Development, Complete/Assign takes you to OSD Peer Review. Now Reject it back to OSD Development. Now Complete it. They want it to go right back to the person last assigned for the OSD Peer R eview rather than making them assign it again.</p>< p>&nbsp;</p>< p>They say it works in the OCN Generation/OCN Peer Review loop just like they want it to, just not here.</p>< p>&nbsp;</p>< p>&nbsp;</p>< p>P.S. They would really like to be able to assign the Developer AND the Peer Review person at the same time so they don't have to get involved anymore until adter the peer review is complete and accepted.</p>
1406 | 1 | Matt Corless | Resolved | recall created two copies for drawing | <p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font size=3 face=Calibri>I recalled a profile that was assigned to an engineer and 2 copies of the profile appeared waiting for OSD Source Data assignment.</font></span></p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font face=Calibri><font size=3><font color="#000000"></font></font></font></span>&nbsp;</p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font face=Calibri><font size=3><font color="#000000">Source: a Todd Garrett email 5/20/2016</font></font></font></span></p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font color="#000000" size=3 face=Calibri></font></span>&nbsp;</p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font color="#000000" size=3 face=Calibri>plb: I'm pretty sure this is a case where we ended up with 2 active tasks rather than two profiles. This&nbsp;might already&nbsp;be fixed.</font></span></p><p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font color="#000000" size=3 face=Calibri><br></font></span></p><p class=MsoNormal style="MARGIN:0in 0in 0pt;"><br></p><p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font color="#000000" size=3 face=Calibri>Matt:&nbsp;</font></span><span style="line-height:1.5em;">It appears the two main issues are the initial recall email being incorrect and the profile not actually changing states when recalled. Also, assigning the recalled profile sent 2 emails (profile was not duplicated, nor were there 2 active tasks)</span></p>
1407 | 1 | Matt Corless | Resolved | Reject to GK needs to send email | <p>When something gets rejected to the Gate Keeper it goes to the ready for state. The Gate Keeper needs to get an email telling them that. Or better yet, have it go to &quot;Assignments&quot; instead of &quot;Ready&quot;.</p>< p>&nbsp;</p>< p>Source: Clarence</p>
1409 | 1 | Matt Corless | Resolved | Rejected to Genarator should allow going back to review (instead of gatekeeper) | <p>Review rejected to generator but when generator was complete it only gives the option to &quot;Complete... send to GK&quot;. Should go back to Reviewer - loop didn't work.</p>< p>&nbsp;</p>< p>Source: Clarence</p>
1410 | 1 | Matt Corless | Resolved | Reject to GK broken (from Ready for OCN Gen) | <p>In the Non-Core OCN process</p>< p>&nbsp;</p>< p>From the &quot;Ready for OCN Generation&quot; the reject to Gate Keeper didn't work. It stayed in the same state.</p>< p>&nbsp;</p>< p>Source: Clarence</p>
1411 | 1 | Matt Corless | Resolved | Assign for OCN generation creates a duplicate profile | <p>In the Non-Core OCN process</p>< p>&nbsp;</p>< p>When assign for OCN generation it created a duplicate profile - see ID 1318 on the live site.&nbsp;</p>< p>Source: Clarence</p>< p>&nbsp;</p>< p>plb: I'm pretty sure what happened was that it ended up with two active tasks rather than two profiles.</p>
1412 | 2 | Matt Corless | Resolved | Reject to GK looses the budget | <p>In the Non-Core OCN process</p>< p>&nbsp;</p>< p>At OCN Generation when rejected back to OCN Gate Keeper it didn't remember the negotiated budget.&nbsp;</p>< p>&nbsp;</p>< p>Source: Clarence</p>
1403 | 2 | Peter Birch | Resolved | Change "High Assembly" to "Next Higher Assembly" or "NHA" on Task Coordination page | <p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font color="#000000" size=3 face=Calibri>On the Task Coordination page, under “Ready for Design Information Assignment”, one of the column headings says, “High Assembly”.&nbsp; It should say, “Next Higher Assembly” or you could shorten it to “NHA”.</font></p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font color="#000000" size=3 face=Calibri></font>&nbsp;</p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font face=Calibri><font size=3><font color="#000000">Source: a Todd Garrett email 5/20/2016</font></font></font></p>
1404 | 2 | Peter Birch | Resolved | Can't cancel drawing from Ready for DI Assignment | <p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font color="#000000" size=3 face=Calibri>I tried to remove a test drawing that was created with a drawing number of “zzzz” located on the Task Coordination screen under “Ready for Design Information Assignment”.&nbsp; I clicked on the drawing and went to the profile screen, at the bottom of the screen, I clicked on “Cancel Drawing”.&nbsp; I received a message stating that the drawing was cancelled, but it still appears in the Task Coordination page and is not listed as Cancelled.</font></p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font color="#000000" size=3 face=Calibri></font>&nbsp;</p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font face=Calibri><font size=3><font color="#000000">Source: a Todd Garrett email 5/20/2016</font></font></font></p>
1405 | 2 | Peter Birch | Resolved | Advance/Assign dialog doesn't save hours (onReady for DI Assignment) | <p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font size=3 face=Calibri>&nbsp;&nbsp;&nbsp;&nbsp; I am on the Task Coordination page, under “Ready for Design Information Assignment”, I open up a drawing and go to the bottom of the screen and press “Advance to Next State &amp; Assign”.&nbsp; This opens up another box that allows me to assign the task for “Government DI” to a Government Engineer.&nbsp; It also allows me to change the hours and the start and end dates for the task.&nbsp; Since we don’t track hours for the external Engineers, I changed the hours from the default of 20 hrs. to 0 hrs. and pressed “Assign Design Information”.&nbsp; There were no errors generated and it looked like it would work.&nbsp; However, the hours assigned for the task did not change to 0 hrs and were left at 20 hrs.</font></span></p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font face=Calibri><font size=3><font color="#000000"></font></font></font></span>&nbsp;</p>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font face=Calibri><font size=3><font color="#000000">Source: a Todd Garrett email 5/20/2016</font></font></font></p></span>< p class=MsoNormal style="MARGIN:0in 0in 0pt;"><span style="COLOR:#1f497d;"><font size=3 face=Calibri></font></span>&nbsp;</p>
1332 | 2 | Peter Birch | Resolved | Remove user dropdown on hours log for engineers / auto-select logged in engineer | <p>When logged in as a normal user and go to the view/edit screen for a profile that has a task assigned to you - specifically a review, there is a user drop down that I don't think should be there that defaults to the first person in the list. I think it should be the user and it should just automatically get put in there without the dropdown.</p>< p>&nbsp;</p>< p>see the attached screen capture</p>
1447 | 2 | Matt Corless | Resolved | Fix logic in Email Types | In TaskEmail.cs the logic in many of the email types does not make sense and often overrides itself.<div><br></div><div>In case EmailTypes.SDAproved the RSD email will always overwrite the OSD email.</div><div>EmailType.RejectSd has a similar issue (currently fixed in a shelveset).&nbsp;</div><div><br></div><div>The bad logic causes many emails to be sent with the wrong text.</div>
1477 | 2 | Matt Corless | Resolved | [Internal] Fix budget tracking throughout the processes | The are many different issues keeping tracking of budgets when profiles are rejected.\<div><br></div><div>protected void m_btnAccept_Command is in three different classes.</div><div>The m_btnAccept_Command method does not make much sense and parts of it are apparently there to fix a larger issue in how budget hours are tracked between tasks.</div><div><br></div>
1487 | 2 | Matt Corless | Resolved | Complete And Assign from DI when assigned to external | Source: Clarence<div><br></div><div>When Design information is assigned to an external person, when he attempts to comple and Assign from DI, it only shows external people for assigning to Development/Generation. When advancing, then assigning, it will properly only show internal people for Development/Generation.</div><div><br></div><div>Matt: should just be the wrong button or wrong modal being made visible in ViewEdit.</div>
1416 | 2 | Matt Corless | Resolved | Accepting peer review looses budget | <p>In the Non-Core OCN process</p>< p>&nbsp;</p>< p>After Accepting OCN Peer Review it went right to &quot;OSD Originator Review&quot; but gave a zero budget.</p>< p>&nbsp;</p>< p>Source: Clarence</p>
1418 | 2 | Peter Birch | Resolved | show nt id on use management page | On the user management page addd the NT ID column as a text box at the beginning
1419 | 2 | Peter Birch | Resolved | Re-Activate a cancelled profile crashed | <p>If there was a cancelled profile and you go to the viewEdit screen for it there is a button that says &quot;Re-Activate&quot;. It was doing a Recall which was crashing because a cancelled profile has no tasks (all tasks have been marked Dead) and Recall needs a current task.</p>< p>&nbsp;</p>< p>Changed code to have a new action called Reactivate that changes the status to onhold - everything works after that</p>
1422 | 2 | Matt Corless | Resolved | Assign Hours to Peer Review | <p>When I assign an Engineer to do OCN Source Data generation for a harness, the software prompts me to put in budgeted hours for the generation task as well as the peer review task.&nbsp; The generation task hours seems to work, but the peer review task seems to go back to some default value (8 hours).</p>< p>&nbsp;</p>< p>Todd Garrett<br></p>
1423 | 2 | Peter Birch | Resolved | Sorting by contract seems to do somethingelse | <p>on the list page, when you click the sort asc or desc glyphs for the contract column it sorts but the sort doesn't make any sense.</p>< p>&nbsp;</p>< p>plb - the problem was it was sorting by ContractVehicle rather than the displayed contract number. Now it sorts by the Contract number then the contract vehicle then whateverelse it was already sorting by</p>
1424 | 2 | Peter Birch | Resolved | can't filter by IsExternal | The admin user management page can't filter the list by the IsExternal field but it can by everything else.
1425 | 2 | Peter Birch | Resolved | Squished taskcoordination progressbars | <p>The TaskCoordination page the engineer progresbars are very squished, the biggest one show fill the entire bar.</p>< p>&nbsp;</p>< p>The problem was that external engineers are not shown on the list but they had the largest number of hours assigned to them.</p>
1426 | 2 | Peter Birch | Resolved | All generator to edit more fields | <p>All the generoator to edit the NHA and the NHA Required fields because these may not be known until later.</p>
1427 | 2 | Peter Birch | Resolved | Assignments not getting logged to Comments | <p>If there was just an assignment it wasn't getting logged to the comments log.</p>< p>&nbsp;</p>< p>Reported by: Todd</p>
1433 | 2 | Peter Birch | Resolved | show base and new dash numbers | <p>On ALL lists on the Task Coordination Page show the basline and new dash numbers</p>< p>&nbsp;</p>< p>Source: Todd</p>
1435 | 2 | Jeremy Stander | Resolved | Keep the Uploaded filename | <p>Keep the original filenames despite EDT maintaining the latest. This will help while the offline process is still going on.</p>< p>&nbsp;</p>< p>6/1/2015</p>
1402 | 2 | Peter Birch | Resolved | Create and make copies - don't copy some fields | <p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><span style=""><span style=""><font color="#000000"><span style="FONT:7pt &quot;Times New Roman&quot;;">&nbsp;</span></font></span></span><font color="#000000" size=3 face=Calibri>When the function to “Create and Make Copies” is used it copies everything except the drawing number and dash numbers.&nbsp; So, on the next screen we have to fill in the drawing number and dash numbers.&nbsp; It should also not copy the “Next Higher Assembly Drawing (NHA)” or the radial button for “NHA OCN Required”.&nbsp; On the screen where we add the information for the drawing number and dash numbers, we should also have fields to fill in the “Next Higher Assembly Drawing (NHA)” and the radial button for “NHA OCN Required”.</font></p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font color="#000000" size=3 face=Calibri></font>&nbsp;</p>< p class=MsoListParagraph style="MARGIN:0in 0in 0pt 29.25pt;TEXT-INDENT:-0.25in;"><font face=Calibri><font size=3><font color="#000000">Source: a Todd Garrett email 5/20/2016</font></font></font></p>